## Summary
OMS BA Project - Tracking Summary
Business requirements | 6
Functional requirements | 17
Non-functional requirements | 10
User stories | 17
Total story points (stories+tasks+bugs) | 139
Test cases | 25
Passed | 21
Failed | 4
Pass rate | 84%
FRs with at least one test case | 17
Requirement coverage (FRs tested / FRs) | 100%
Open bugs | 5
Sheets: Stakeholders ¦ Requirements ¦ User Stories ¦ Jira Backlog ¦ Sprint Plan ¦ UAT ¦ RTM

## Stakeholders
Stakeholder | Role | Influence | Interest | Key needs / concerns | Engagement approach
Customer | End user placing and tracking orders | High | Medium | Fast delivery, no payment failures, clear status, easy refunds | Keep informed (notifications); validated through surveys/UAT personas
Customer Support | Handles complaints and tickets | Medium | High | Single view of order, fewer 'where is my order' tickets | Consult; process owner for FR-14; UAT participant
Operations Manager | Owns delivery SLA and fulfilment performance | High | High | SLA visibility, early delay alerts, carrier accountability | Manage closely; business sponsor
Warehouse Team | Pick, pack, dispatch, stock counts | Medium | High | Accurate stock, clear pick lists, realistic cut-off times | Consult; UAT participant for FR-08/15
Finance | Payments, refunds, reconciliation | High | Medium | Correct refunds, reconciliation, reduced revenue leakage | Manage closely; sign-off on FR-13
Product Manager | Owns roadmap and priorities | High | High | Business value, scope control, release timing | Manage closely; approves BRD and backlog
Developer | Builds the solution | Low | Medium | Clear, testable requirements; stable scope | Keep informed; refinement sessions
QA | Verifies the solution | Low | Medium | Testable acceptance criteria, traceability | Keep informed; owns test cases and RTM execution
Payment Gateway (external) | Third-party payment processing | Medium | Medium | Correct API usage, idempotency, low failure/timeouts | Monitor; SLA/contract; integration spec

## Requirements
ID | Type | Requirement | Linked BR | Priority
BR-01 | Business Requirement | Reduce late deliveries (baseline 24.8% delayed vs. promised date; target <=10%)
BR-02 | Business Requirement | Recover revenue lost to failed payments (baseline 3.0% of orders lost; Net Banking 11.3% attempt failure)
BR-03 | Business Requirement | Make inventory accurate in real time (baseline 26% of SKUs mismatched at audit; target <=5%)
BR-04 | Business Requirement | Give customers and staff full order-status visibility (21% of tickets are 'where is my order')
BR-05 | Business Requirement | Cut avoidable support tickets (baseline 1,081 tickets on 6,000 orders; target -35%)
BR-06 | Business Requirement | Make cancellations, returns and refunds fast and transparent (137 refunds pending; avg refund-delay ticket 4.7 days)
FR-01 | Functional | Create an order as 'Confirmed' only after payment success (or COD confirmation); failed payment leaves order in 'Payment Pending'. | BR-02 | High
FR-02 | Functional | Allow payment retry and switching to an alternate method within 30 minutes without re-entering the cart; payments must be idempotent (no double charge). | BR-02 | High
FR-03 | Functional | Check live stock and reserve quantity at checkout; release the reservation if payment fails or times out. | BR-03 | High
FR-04 | Functional | Block checkout for out-of-stock items and offer 'Notify me' / similar products. | BR-03 | High
FR-05 | Functional | Maintain a single order status lifecycle (Placed > Confirmed > Packed > Shipped > Out for Delivery > Delivered, plus Cancelled/Returned) with a timestamp for every change. | BR-04 | High
FR-06 | Functional | Provide a customer order-tracking page showing current status and estimated delivery date. | BR-04 | High
FR-07 | Functional | Send proactive SMS/e-mail/WhatsApp notifications on every key status change and on any predicted delay. | BR-04 | Medium
FR-08 | Functional | Auto-allocate each order to the nearest warehouse holding stock; alert the warehouse if pick/pack exceeds 24 hours. | BR-01 | High
FR-09 | Functional | Auto-assign a carrier by pincode and performance score and ingest carrier tracking events. | BR-01 | Medium
FR-10 | Functional | Flag any order at risk of missing its promised date (SLA breach) to Operations in real time. | BR-01 | High
FR-11 | Functional | Let customers cancel self-service until the order is shipped; trigger refund automatically. | BR-06 | High
FR-12 | Functional | Let customers raise a return request within 7 days of delivery with reason code and pickup slot. | BR-06 | Medium
FR-13 | Functional | Automate refunds to the original payment source within 5 business days of return QC pass, with visible refund status. | BR-06 | High
FR-14 | Functional | Give support agents an 'Order 360' view (payment, inventory, shipment, history) on one screen. | BR-05 | Medium
FR-15 | Functional | Reconcile system stock with warehouse cycle counts and log every adjustment with a reason. | BR-03 | Medium
FR-16 | Functional | Provide operations/management dashboards for order volume, SLA, cancellations, payment failures, returns and complaints. | BR-01 | Medium
FR-17 | Functional | Keep an audit log of all order, payment and inventory state changes (who/what/when). | BR-04 | Low
NFR-01 | Non-Functional | [Performance] Checkout and order-status pages respond in <=2 seconds for 95% of requests at 500 concurrent users.
NFR-02 | Non-Functional | [Availability] 99.9% monthly uptime for order placement; planned maintenance outside 1-5 AM IST window only.
NFR-03 | Non-Functional | [Scalability] Handle 3x current peak order volume (festival sales) without code change.
NFR-04 | Non-Functional | [Security] PCI-DSS compliant payment handling; card data never stored in OMS; role-based access control.
NFR-05 | Non-Functional | [Data privacy] Customer PII encrypted at rest and in transit; compliant with India's DPDP Act 2023.
NFR-06 | Non-Functional | [Reliability] No order lost on payment-gateway or carrier API failure; retry queue with dead-letter alerts.
NFR-07 | Non-Functional | [Auditability] All status changes retained for 7 years and searchable by order ID.
NFR-08 | Non-Functional | [Usability] Customer can complete tracking/cancellation in <=3 clicks; mobile-first responsive UI.
NFR-09 | Non-Functional | [Integration] REST APIs with versioning for payment gateway, carriers, WMS and notification services.
NFR-10 | Non-Functional | [Reporting latency] Dashboards refresh at most every 15 minutes.

## User Stories
Story ID | Epic | FR | User Story | Acceptance Criteria | Priority | Story Points | Sprint
US-01 | EP-1 | FR-01 | As a customer, I want my order confirmed only after my payment succeeds so that I am never charged for an order that doesn't exist. | AC1: Given payment succeeds, when the gateway returns success, then order status = Confirmed and confirmation is sent within 1 minute. AC2: Given payment fails, when the gateway returns failure, then order stays 'Payment Pending' and is not sent to the warehouse. | High | 5 | Sprint 1
US-02 | EP-1 | FR-02 | As a customer, I want to retry or switch my payment method after a failure so that I don't lose my cart. | AC1: Given a failed payment, when I choose another method within 30 minutes, then the same cart and price are retained. AC2: Given I retry twice quickly, then I am charged only once (idempotency). | High | 8 | Sprint 1
US-03 | EP-2 | FR-03 | As a customer, I want stock checked and held while I pay so that the item I buy is actually available. | AC1: Given stock >= quantity, when I start payment, then quantity is reserved for 15 minutes. AC2: Given payment fails or times out, then the reservation is released automatically. | High | 8 | Sprint 1
US-04 | EP-2 | FR-04 | As a customer, I want to see out-of-stock items clearly so that I can pick an alternative or get notified. | AC1: Given stock = 0, then 'Add to cart' is disabled and 'Notify me' is shown. AC2: Given an item becomes out of stock during checkout, then the order is blocked with a clear message. | High | 3 | Sprint 1
US-05 | EP-3 | FR-05 | As an operations manager, I want a single status lifecycle with timestamps so that I can see where every order is. | AC1: Given any status change, then the new status and timestamp are stored. AC2: Given an invalid transition (e.g. Delivered to Packed), then the system rejects it. | High | 5 | Sprint 2
US-06 | EP-3 | FR-06 | As a customer, I want to track my order status so that I know when my order will arrive. | AC1: Given a logged-in customer, when they open 'My Orders', then they see current status and estimated delivery date. AC2: Given the carrier updates status, then the tracking page reflects it within 15 minutes. | High | 5 | Sprint 2
US-07 | EP-3 | FR-07 | As a customer, I want proactive updates on my order so that I don't have to contact support. | AC1: Given a status change (Shipped, Out for Delivery, Delivered), then an SMS/e-mail is sent within 5 minutes. AC2: Given an order is predicted to be late, then I am notified with a revised date. | Medium | 5 | Sprint 3
US-08 | EP-4 | FR-08 | As a warehouse executive, I want orders auto-allocated to the nearest stocked warehouse so that dispatch is faster. | AC1: Given an order is confirmed, then it is assigned to the nearest warehouse with stock. AC2: Given pick/pack is not complete in 24 hours, then the warehouse manager is alerted. | High | 8 | Sprint 2
US-09 | EP-4 | FR-09 | As an operations manager, I want carriers assigned by pincode performance so that late deliveries reduce. | AC1: Given a shipment is created, then the carrier with the best on-time score for that pincode is assigned. AC2: Given the carrier posts a tracking event, then it is stored against the shipment. | Medium | 8 | Sprint 3
US-10 | EP-4 | FR-10 | As an operations manager, I want to be alerted when an order may miss its promised date so that I can intervene. | AC1: Given an order not shipped 48 hours after confirmation, then it is flagged 'At Risk'. AC2: Given an order is delayed, then it appears on the Ops dashboard with the delay reason. | High | 5 | Sprint 2
US-11 | EP-5 | FR-11 | As a customer, I want to cancel an order before it ships so that I don't pay for something I no longer need. | AC1: Given status is before Shipped, when I cancel, then status = Cancelled and a refund is initiated. AC2: Given status is Shipped or later, then the Cancel button is not available. | High | 5 | Sprint 3
US-12 | EP-5 | FR-12 | As a customer, I want to raise a return request online so that I can send back a wrong or damaged item easily. | AC1: Given an order delivered within the last 7 days, then 'Return' is available with reason selection. AC2: Given I submit a return, then a pickup slot is confirmed. | Medium | 5 | Sprint 3
US-13 | EP-5 | FR-13 | As a finance executive, I want refunds automated and tracked so that customers are paid on time and books reconcile. | AC1: Given a return passes QC, then a refund to the original source is initiated within 1 business day. AC2: Given a refund is pending > 5 business days, then it appears on the Finance exception report. | High | 8 | Sprint 4
US-14 | EP-6 | FR-14 | As a support agent, I want an Order 360 view so that I can resolve queries without switching systems. | AC1: Given an order ID, then payment, inventory, shipment and history are visible on one screen. AC2: Given I add a note, then it is logged with my user ID and time. | Medium | 5 | Sprint 4
US-15 | EP-2 | FR-15 | As a warehouse manager, I want stock reconciled after cycle counts so that system stock matches shelf stock. | AC1: Given a physical count differs from system stock, then an adjustment is logged with reason and approver. AC2: Given adjustment is approved, then available stock updates immediately. | Medium | 5 | Sprint 4
US-16 | EP-6 | FR-16 | As a product manager, I want an operations dashboard so that I can track SLA, cancellations, payments and returns. | AC1: Given the dashboard is opened, then it shows the 7 agreed KPIs filtered by date, warehouse and category. AC2: Given new data arrives, then the dashboard refreshes within 15 minutes. | Medium | 8 | Sprint 4
US-17 | EP-6 | FR-17 | As an auditor, I want every status change logged so that disputes can be investigated. | AC1: Given any order, payment or inventory change, then who/what/when is logged and cannot be edited. | Low | 3 | Sprint 4

## Jira Backlog
Key | Issue Type | Epic | Parent / Linked | Summary | Priority | Story Points | Sprint | Assignee (role) | Status
EP-1 | Epic | EP-1 |  | Checkout & Payment Reliability | High |  |  | Product Manager | In Progress
EP-2 | Epic | EP-2 |  | Inventory Accuracy | High |  |  | Product Manager | In Progress
EP-3 | Epic | EP-3 |  | Order Tracking & Notifications | High |  |  | Product Manager | In Progress
EP-4 | Epic | EP-4 |  | Fulfilment & Delivery SLA | High |  |  | Product Manager | In Progress
EP-5 | Epic | EP-5 |  | Cancellation, Returns & Refunds | High |  |  | Product Manager | In Progress
EP-6 | Epic | EP-6 |  | Support Tools, Audit & Analytics | High |  |  | Product Manager | In Progress
US-01 | Story | EP-1 | FR-01 | customer, I want my order confirmed only after my payment succeeds | High | 5 | Sprint 1 | Dev Team | To Do
US-02 | Story | EP-1 | FR-02 | customer, I want to retry or switch my payment method after a failure | High | 8 | Sprint 1 | Dev Team | To Do
US-03 | Story | EP-2 | FR-03 | customer, I want stock checked and held while I pay | High | 8 | Sprint 1 | Dev Team | To Do
US-04 | Story | EP-2 | FR-04 | customer, I want to see out-of-stock items clearly | High | 3 | Sprint 1 | Dev Team | To Do
US-05 | Story | EP-3 | FR-05 | operations manager, I want a single status lifecycle with timestamps | High | 5 | Sprint 2 | Dev Team | To Do
US-06 | Story | EP-3 | FR-06 | customer, I want to track my order status | High | 5 | Sprint 2 | Dev Team | To Do
US-07 | Story | EP-3 | FR-07 | customer, I want proactive updates on my order | Medium | 5 | Sprint 3 | Dev Team | To Do
US-08 | Story | EP-4 | FR-08 | warehouse executive, I want orders auto-allocated to the nearest stocked warehouse | High | 8 | Sprint 2 | Dev Team | To Do
US-09 | Story | EP-4 | FR-09 | operations manager, I want carriers assigned by pincode performance | Medium | 8 | Sprint 3 | Dev Team | To Do
US-10 | Story | EP-4 | FR-10 | operations manager, I want to be alerted when an order may miss its promised date | High | 5 | Sprint 2 | Dev Team | To Do
US-11 | Story | EP-5 | FR-11 | customer, I want to cancel an order before it ships | High | 5 | Sprint 3 | Dev Team | To Do
US-12 | Story | EP-5 | FR-12 | customer, I want to raise a return request online | Medium | 5 | Sprint 3 | Dev Team | To Do
US-13 | Story | EP-5 | FR-13 | finance executive, I want refunds automated and tracked | High | 8 | Sprint 4 | Dev Team | To Do
US-14 | Story | EP-6 | FR-14 | support agent, I want an Order 360 view | Medium | 5 | Sprint 4 | Dev Team | To Do
US-15 | Story | EP-2 | FR-15 | warehouse manager, I want stock reconciled after cycle counts | Medium | 5 | Sprint 4 | Dev Team | To Do
US-16 | Story | EP-6 | FR-16 | product manager, I want an operations dashboard | Medium | 8 | Sprint 4 | Dev Team | To Do
US-17 | Story | EP-6 | FR-17 | auditor, I want every status change logged | Low | 3 | Sprint 4 | Dev Team | To Do
TSK-01 | Task | EP-1 | US-01 | Define order & payment state machine (BA/Dev) | High | 2 | Sprint 1 | Developer | Done
TSK-02 | Task | EP-1 | US-02 | Integrate payment gateway retry API and idempotency key | High | 5 | Sprint 1 | Developer | In Progress
TSK-03 | Task | EP-2 | US-03 | Build stock reservation service with 15-min expiry | High | 5 | Sprint 1 | Developer | In Progress
TSK-04 | Task | EP-1 | US-01 | Write UAT cases for payment success/failure | Medium | 2 | Sprint 1 | QA | To Do
TSK-05 | Task | EP-3 | US-06 | Design order-tracking wireframe and get PM sign-off | Medium | 2 | Sprint 2 | Business Analyst | To Do
TSK-06 | Task | EP-4 | US-08 | Document warehouse allocation rules (nearest-stock logic) | High | 3 | Sprint 2 | Business Analyst | To Do
TSK-07 | Task | EP-3 | US-07 | Select notification provider and approve message templates | Medium | 3 | Sprint 3 | Product Manager | To Do
TSK-08 | Task | EP-6 | US-16 | Build KPI data model and Power BI dashboard v1 | Medium | 5 | Sprint 4 | Business Analyst | To Do
BUG-01 | Bug | EP-1 | US-02 | Customer charged twice when payment retried within 5 seconds | Critical | 3 | Sprint 1 | Developer | Open
BUG-02 | Bug | EP-2 | US-03 | Reservation not released when payment times out | High | 3 | Sprint 1 | Developer | Open
BUG-03 | Bug | EP-3 | US-06 | Tracking page shows 'Shipped' after order is delivered | High | 2 | Sprint 2 | Developer | Open
BUG-04 | Bug | EP-5 | US-11 | Cancel button visible after order is shipped | Medium | 2 | Sprint 3 | Developer | Open
BUG-05 | Bug | EP-5 | US-13 | Refund amount excludes shipping fee for cancelled orders | High | 3 | Sprint 4 | Developer | Open

## Sprint Plan
Sprint | Duration | Goal | Stories | Total Story Points | Bugs open
Sprint 1 | Weeks 1-2 | Payment & inventory foundation (checkout reliability) | 4 | 44 | 2
Sprint 2 | Weeks 3-4 | Status lifecycle, tracking page, allocation, SLA alerts | 4 | 30 | 1
Sprint 3 | Weeks 5-6 | Notifications, carrier assignment, cancellation, returns | 4 | 28 | 1
Sprint 4 | Weeks 7-8 | Refund automation, support 360, audit, dashboard, UAT & go-live prep | 5 | 37 | 1
Total |  |  | 17 | 139 | 5

## UAT
Test Case ID | FR | User Story | Scenario | Steps / Precondition | Expected Result | Actual Result | Status | Defect ID
TC-01 | FR-01 | US-01 | Successful payment (UPI) | Cart with in-stock item; pay via UPI success | Order created, status Confirmed, confirmation sent | Order created, status Confirmed, confirmation sent | Pass
TC-02 | FR-01 | US-01 | Failed payment | Cart; gateway returns failure | Order not confirmed; stays Payment Pending | Order not confirmed; stays Payment Pending | Pass
TC-03 | FR-02 | US-02 | Retry with different method | After TC-02 choose Credit Card within 30 min | Same cart retained; order Confirmed on success | Same cart retained; order Confirmed | Pass
TC-04 | FR-02 | US-02 | Double-click on Pay (idempotency) | Click Pay twice within 5 seconds | Customer charged once | Customer charged twice | Fail | BUG-01
TC-05 | FR-03 | US-03 | Stock reserved during payment | Qty 1 of last unit; start payment | Unit reserved for 15 min; second buyer sees out of stock | Unit reserved; second buyer blocked | Pass
TC-06 | FR-03 | US-03 | Reservation release on timeout | Start payment, abandon for 16 min | Reservation released; stock available again | Stock still shown reserved after 16 min | Fail | BUG-02
TC-07 | FR-04 | US-04 | Out-of-stock product | Open product with stock = 0 | Order blocked; 'Notify me' shown | Order blocked; 'Notify me' shown | Pass
TC-08 | FR-04 | US-04 | Stock runs out during checkout | Two users buy last unit simultaneously | Second order blocked with message | Second order blocked with message | Pass
TC-09 | FR-05 | US-05 | Valid status transition | Move Packed to Shipped | Status updated with timestamp | Status updated with timestamp | Pass
TC-10 | FR-05 | US-05 | Invalid status transition | Try Delivered to Packed | System rejects the change | System rejects the change | Pass
TC-11 | FR-06 | US-06 | Customer tracks order | Open My Orders for a shipped order | Shows current status and ETA | Shows current status and ETA | Pass
TC-12 | FR-06 | US-06 | Tracking after delivery | Carrier posts Delivered | Tracking page shows Delivered | Tracking page still shows Shipped | Fail | BUG-03
TC-13 | FR-07 | US-07 | Shipped notification | Order moves to Shipped | SMS/e-mail sent within 5 minutes | SMS/e-mail sent within 5 minutes | Pass
TC-14 | FR-08 | US-08 | Warehouse auto-allocation | Confirm order from Delhi with stock in Delhi and Mumbai | Assigned to Delhi warehouse | Assigned to Delhi warehouse | Pass
TC-15 | FR-09 | US-09 | Carrier assignment by pincode | Create shipment to a pincode with carrier scores | Best-scoring carrier assigned | Best-scoring carrier assigned | Pass
TC-16 | FR-10 | US-10 | Delay flag | Order Confirmed, not shipped for 49 hours | Flagged 'At Risk' on Ops dashboard | Flagged 'At Risk' on Ops dashboard | Pass
TC-17 | FR-11 | US-11 | Cancel before shipment | Cancel a Confirmed order | Status Cancelled; refund initiated | Status Cancelled; refund initiated | Pass
TC-18 | FR-11 | US-11 | Cancel after shipment | Open a Shipped order | Cancel option not available | Cancel option visible | Fail | BUG-04
TC-19 | FR-12 | US-12 | Return within window | Delivered 3 days ago; raise return | Return accepted; pickup slot confirmed | Return accepted; pickup slot confirmed | Pass
TC-20 | FR-12 | US-12 | Return outside window | Delivered 10 days ago; raise return | Return rejected with policy message | Return rejected with policy message | Pass
TC-21 | FR-13 | US-13 | Refund after QC pass | Return QC = pass | Refund to original source within 1 business day | Refund initiated to original source | Pass
TC-22 | FR-14 | US-14 | Order 360 view | Agent searches order ID | Payment, shipment, inventory and history shown | Payment, shipment, inventory and history shown | Pass
TC-23 | FR-15 | US-15 | Inventory adjustment | Cycle count differs from system | Adjustment logged with reason/approver; stock updated | Adjustment logged with reason/approver; stock updated | Pass
TC-24 | FR-16 | US-16 | Dashboard refresh | Load new day of data | KPIs refresh within 15 minutes | KPIs refreshed in 9 minutes | Pass
TC-25 | FR-17 | US-17 | Audit log | Change an order status | Log entry with user, time, old and new value | Log entry with user, time, old and new value | Pass
Note: UAT executed on a hypothetical prototype for portfolio purposes; actual results are illustrative to demonstrate defect logging and traceability.

## RTM
Business Requirement | Functional Requirement | User Story | Test Case | Test Result (live from UAT) | Defect
BR-02 - Recover revenue lost to failed payments | FR-01 - Create an order as 'Confirmed' only after payment success (or COD confirmation); failed payment leaves order in 'Payment Pending'. | US-01 | TC-01 | Pass
BR-02 - Recover revenue lost to failed payments | FR-01 - Create an order as 'Confirmed' only after payment success (or COD confirmation); failed payment leaves order in 'Payment Pending'. | US-01 | TC-02 | Pass
BR-02 - Recover revenue lost to failed payments | FR-02 - Allow payment retry and switching to an alternate method within 30 minutes without re-entering the cart; payments must be idempotent (no double charge). | US-02 | TC-03 | Pass
BR-02 - Recover revenue lost to failed payments | FR-02 - Allow payment retry and switching to an alternate method within 30 minutes without re-entering the cart; payments must be idempotent (no double charge). | US-02 | TC-04 | Fail | BUG-01
BR-03 - Make inventory accurate in real time | FR-03 - Check live stock and reserve quantity at checkout; release the reservation if payment fails or times out. | US-03 | TC-05 | Pass
BR-03 - Make inventory accurate in real time | FR-03 - Check live stock and reserve quantity at checkout; release the reservation if payment fails or times out. | US-03 | TC-06 | Fail | BUG-02
BR-03 - Make inventory accurate in real time | FR-04 - Block checkout for out-of-stock items and offer 'Notify me' / similar products. | US-04 | TC-07 | Pass
BR-03 - Make inventory accurate in real time | FR-04 - Block checkout for out-of-stock items and offer 'Notify me' / similar products. | US-04 | TC-08 | Pass
BR-04 - Give customers and staff full order-status visibility | FR-05 - Maintain a single order status lifecycle (Placed > Confirmed > Packed > Shipped > Out for Delivery > Delivered, plus Cancelled/Returned) with a timestamp for every change. | US-05 | TC-09 | Pass
BR-04 - Give customers and staff full order-status visibility | FR-05 - Maintain a single order status lifecycle (Placed > Confirmed > Packed > Shipped > Out for Delivery > Delivered, plus Cancelled/Returned) with a timestamp for every change. | US-05 | TC-10 | Pass
BR-04 - Give customers and staff full order-status visibility | FR-06 - Provide a customer order-tracking page showing current status and estimated delivery date. | US-06 | TC-11 | Pass
BR-04 - Give customers and staff full order-status visibility | FR-06 - Provide a customer order-tracking page showing current status and estimated delivery date. | US-06 | TC-12 | Fail | BUG-03
BR-04 - Give customers and staff full order-status visibility | FR-07 - Send proactive SMS/e-mail/WhatsApp notifications on every key status change and on any predicted delay. | US-07 | TC-13 | Pass
BR-01 - Reduce late deliveries | FR-08 - Auto-allocate each order to the nearest warehouse holding stock; alert the warehouse if pick/pack exceeds 24 hours. | US-08 | TC-14 | Pass
BR-01 - Reduce late deliveries | FR-09 - Auto-assign a carrier by pincode and performance score and ingest carrier tracking events. | US-09 | TC-15 | Pass
BR-01 - Reduce late deliveries | FR-10 - Flag any order at risk of missing its promised date (SLA breach) to Operations in real time. | US-10 | TC-16 | Pass
BR-06 - Make cancellations, returns and refunds fast and transparent | FR-11 - Let customers cancel self-service until the order is shipped; trigger refund automatically. | US-11 | TC-17 | Pass
BR-06 - Make cancellations, returns and refunds fast and transparent | FR-11 - Let customers cancel self-service until the order is shipped; trigger refund automatically. | US-11 | TC-18 | Fail | BUG-04
BR-06 - Make cancellations, returns and refunds fast and transparent | FR-12 - Let customers raise a return request within 7 days of delivery with reason code and pickup slot. | US-12 | TC-19 | Pass
BR-06 - Make cancellations, returns and refunds fast and transparent | FR-12 - Let customers raise a return request within 7 days of delivery with reason code and pickup slot. | US-12 | TC-20 | Pass
BR-06 - Make cancellations, returns and refunds fast and transparent | FR-13 - Automate refunds to the original payment source within 5 business days of return QC pass, with visible refund status. | US-13 | TC-21 | Pass
BR-05 - Cut avoidable support tickets | FR-14 - Give support agents an 'Order 360' view (payment, inventory, shipment, history) on one screen. | US-14 | TC-22 | Pass
BR-03 - Make inventory accurate in real time | FR-15 - Reconcile system stock with warehouse cycle counts and log every adjustment with a reason. | US-15 | TC-23 | Pass
BR-01 - Reduce late deliveries | FR-16 - Provide operations/management dashboards for order volume, SLA, cancellations, payment failures, returns and complaints. | US-16 | TC-24 | Pass
BR-04 - Give customers and staff full order-status visibility | FR-17 - Keep an audit log of all order, payment and inventory state changes (who/what/when). | US-17 | TC-25 | Pass